## Effort Estimation
Module | Feature | Subfeature | Frontend Effort | Frontend Buffer | Frontend Testing | Backend Effort | Backend Buffer | Backend Testing
User Authentication | User Registration | Frontend UI/UX Implementation | 5 | 1 | 0.9 | 3 | 0.6 | 0.54
User Authentication | User Registration | Backend API Implementation | 0 | 0 | 0 | 5 | 1 | 0.9
User Authentication | User Registration | Database Integration | 0 | 0 | 0 | 3 | 0.6 | 0.54
User Authentication | User Login | Frontend UI/UX Implementation | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
User Authentication | User Login | Backend API Implementation | 0 | 0 | 0 | 2 | 0.4 | 0.36
Product Catalog | Product Listing | Frontend UI/UX Implementation | 7 | 1.4 | 1.26 | 5 | 1 | 0.9
Product Catalog | Product Listing | Backend API Implementation | 0 | 0 | 0 | 7 | 1.4 | 1.26
Product Catalog | Product Listing | Database Integration | 0 | 0 | 0 | 5 | 1 | 0.9
Product Catalog | Product Detail | Frontend UI/UX Implementation | 5 | 1 | 0.9 | 3 | 0.6 | 0.54
Product Catalog | Product Detail | Backend API Implementation | 0 | 0 | 0 | 3 | 0.6 | 0.54
Total |  | Total | 20 | 4 | 3.6 | 38 | 7.6 | 6.84
|  | Units | days | days | days | days | days | days

## Cost Summary
Item | Effort in Days | Rate per hour (IN INR) | Pricing
Frontend | 26.4 | 15 | ₹3,168.00
Backend | 50.16 | 16 | ₹6,420.48
Testing | 3.96 | 12 | ₹380.16
Total |  |  | ₹9,968.64