## Effort Estimation
Module | Feature | Subfeature | Frontend Effort | Frontend Buffer | Frontend Testing | Backend Effort | Backend Buffer | Backend Testing
User Authentication | User Registration | Frontend Implementation | 5 | 1 | 0.9 | 7 | 1.4 | 1.26
User Authentication | User Registration | Email Verification | 3 | 0.6 | 0.54 | 4 | 0.8 | 0.72
User Authentication | Login | Frontend Implementation | 3 | 0.6 | 0.54 | 4 | 0.8 | 0.72
User Authentication | Login | Session Management | 2 | 0.4 | 0.36 | 3 | 0.6 | 0.54
Product Catalog | Product Listing | Frontend Implementation | 7 | 1.4 | 1.26 | 10 | 2 | 1.8
Product Catalog | Product Listing | Filtering and Sorting | 5 | 1 | 0.9 | 7 | 1.4 | 1.26
Product Catalog | Product Details | Frontend Implementation | 5 | 1 | 0.9 | 7 | 1.4 | 1.26
Product Catalog | Product Details | Add to Cart | 3 | 0.6 | 0.54 | 4 | 0.8 | 0.72
Total |  | Total | 33 | 6.6 | 5.94 | 46 | 9.2 | 8.28
|  | Units | days | days | days | days | days | days

## Cost Summary
Item | Effort in Days | Rate per hour (IN INR) | Pricing
Frontend | 43.56 | 15 | ₹5,227.20
Backend | 60.72 | 16 | ₹7,772.16
Testing | 6.534 | 12 | ₹627.26
Total |  |  | ₹13,626.62