## Effort Estimation
Module | Feature | Subfeature | Frontend Effort | Frontend Buffer | Frontend Testing | Backend Effort | Backend Buffer | Backend Testing
User Authentication | User Registration | Frontend Implementation | 5 | 1 | 0.9 | 3 | 0.6 | 0.54
User Authentication | User Registration | Email Verification | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
User Authentication | User Registration | Password Recovery | 4 | 0.8 | 0.72 | 3 | 0.6 | 0.54
User Authentication | User Login | Frontend Implementation | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
User Authentication | User Login | Session Management | 2 | 0.4 | 0.36 | 2 | 0.4 | 0.36
Product Catalog | Product Listing | Frontend Implementation | 7 | 1.4 | 1.26 | 5 | 1 | 0.9
Product Catalog | Product Listing | Product Search | 5 | 1 | 0.9 | 4 | 0.8 | 0.72
Product Catalog | Product Listing | Pagination | 2 | 0.4 | 0.36 | 2 | 0.4 | 0.36
Product Catalog | Product Details | Frontend Implementation | 5 | 1 | 0.9 | 3 | 0.6 | 0.54
Product Catalog | Product Details | Reviews and Ratings | 4 | 0.8 | 0.72 | 3 | 0.6 | 0.54
Total |  | Total | 40 | 8 | 7.2 | 29 | 5.8 | 5.22
|  | Units | days | days | days | days | days | days

## Cost Summary
Item | Effort in Days | Rate per hour (IN INR) | Pricing
Frontend | 52.8 | 15 | ₹6,336.00
Backend | 38.28 | 16 | ₹4,899.84
Testing | 7.92 | 12 | ₹760.32
Total |  |  | ₹11,996.16