## Effort Estimation
Module | Feature | Subfeature | Frontend Effort | Frontend Buffer | Frontend Testing | Backend Effort | Backend Buffer | Backend Testing
Frontend Development | User Authentication | Login Page | 5 | 1 | 0.9 | 3 | 0.6 | 0.54
Frontend Development | User Authentication | Registration Page | 5 | 1 | 0.9 | 3 | 0.6 | 0.54
Frontend Development | User Authentication | Password Recovery | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
Frontend Development | Dashboard | Main Layout | 7 | 1.4 | 1.26 | 5 | 1 | 0.9
Frontend Development | Dashboard | User Profile | 5 | 1 | 0.9 | 3 | 0.6 | 0.54
Frontend Development | Dashboard | Settings | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
Backend Development | User Management | User Registration | 0 | 0 | 0 | 5 | 1 | 0.9
Backend Development | User Management | User Authentication | 0 | 0 | 0 | 7 | 1.4 | 1.26
Backend Development | User Management | User Profile | 0 | 0 | 0 | 4 | 0.8 | 0.72
Backend Development | Data Storage | Database Design | 0 | 0 | 0 | 10 | 2 | 1.8
Backend Development | Data Storage | Data Mapping | 0 | 0 | 0 | 8 | 1.6 | 1.44
Total |  | Total | 28 | 5.6 | 5.04 | 52 | 10.4 | 9.36
|  | Units | days | days | days | days | days | days

## Cost Summary
Item | Effort in Days | Rate per hour (IN INR) | Pricing
Frontend | 36.96 | 15 | ₹4,435.20
Backend | 68.64 | 16 | ₹8,785.92
Testing | 5.544 | 12 | ₹532.22
Total |  |  | ₹13,753.34