## Effort Estimation
Module | Feature | Subfeature | Frontend Effort | Frontend Buffer | Frontend Testing | Backend Effort | Backend Buffer | Backend Testing
User Authentication | User Registration | Form Implementation | 5 | 1 | 0.9 | 7 | 1.4 | 1.26
User Authentication | User Registration | Email Verification | 3 | 0.6 | 0.54 | 4 | 0.8 | 0.72
User Authentication | User Registration | Password Encryption | 2 | 0.4 | 0.36 | 3 | 0.6 | 0.54
User Authentication | User Login | Form Implementation | 4 | 0.8 | 0.72 | 5 | 1 | 0.9
User Authentication | User Login | Session Management | 3 | 0.6 | 0.54 | 4 | 0.8 | 0.72
Product Catalog | Product Listing | Product Card Design | 8 | 1.6 | 1.44 | 5 | 1 | 0.9
Product Catalog | Product Listing | Filtering and Sorting | 6 | 1.2 | 1.08 | 4 | 0.8 | 0.72
Product Catalog | Product Search | Search Bar Implementation | 5 | 1 | 0.9 | 6 | 1.2 | 1.08
Product Catalog | Product Search | Autocomplete Suggestions | 4 | 0.8 | 0.72 | 3 | 0.6 | 0.54
Shopping Cart | Add to Cart | Add Product to Cart | 4 | 0.8 | 0.72 | 3 | 0.6 | 0.54
Shopping Cart | Add to Cart | Cart Update | 5 | 1 | 0.9 | 4 | 0.8 | 0.72
Shopping Cart | Cart Summary | Product Quantity Display | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
Shopping Cart | Cart Summary | Total Cost Calculation | 4 | 0.8 | 0.72 | 3 | 0.6 | 0.54
Shopping Cart | Remove from Cart | Remove Product from Cart | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
Checkout | Shipping Address | Address Form Implementation | 6 | 1.2 | 1.08 | 4 | 0.8 | 0.72
Checkout | Payment | Payment Gateway Integration | 8 | 1.6 | 1.44 | 10 | 2 | 1.8
Checkout | Payment | Order Confirmation | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
Total |  | Total | 76 | 15.2 | 13.68 | 71 | 14.2 | 12.78
|  | Units | days | days | days | days | days | days

## Cost Summary
Item | Effort in Days | Rate per hour (IN INR) | Pricing
Frontend | 100.32 | 15 | ₹12,038.40
Backend | 93.72 | 16 | ₹11,996.16
Testing | 15.02 | 12 | ₹1,441.92
Total |  |  | ₹25,476.48