## Effort Estimation
Module | Feature | Subfeature | Frontend Effort | Frontend Buffer | Frontend Testing | Backend Effort | Backend Buffer | Backend Testing
AI-Powered Proficiency Assessment | Diagnostic Test at Onboarding | Diagnostic Test Implementation | 7 | 1.4 | 1.26 | 10 | 2 | 1.8
AI-Powered Proficiency Assessment | Diagnostic Test at Onboarding | Proficiency Level Evaluation | 5 | 1 | 0.9 | 8 | 1.6 | 1.44
AI-Powered Proficiency Assessment | Ongoing Performance Analysis | User Performance Tracking | 6 | 1.2 | 1.08 | 8 | 1.6 | 1.44
AI-Powered Proficiency Assessment | Ongoing Performance Analysis | Proficiency Level Adjustment | 5 | 1 | 0.9 | 7 | 1.4 | 1.26
Adaptive Lesson Planning | Personalized Lesson Plans | User Weak Area Identification | 5 | 1 | 0.9 | 7 | 1.4 | 1.26
Adaptive Lesson Planning | Personalized Lesson Plans | Lesson Plan Generation | 8 | 1.6 | 1.44 | 10 | 2 | 1.8
Adaptive Lesson Planning | Interactive Lesson Display | Lesson Layout Design | 10 | 2 | 1.8 | 2 | 0.4 | 0.36
Adaptive Lesson Planning | Interactive Lesson Display | Lesson Interactivity Implementation | 15 | 3 | 2.7 | 3 | 0.6 | 0.54
Conversational AI for Real-Life Dialogues | Real-World Conversation Simulation | Conversation Scenario Design | 10 | 2 | 1.8 | 12 | 2.4 | 2.16
Conversational AI for Real-Life Dialogues | Real-World Conversation Simulation | Conversation Implementation | 15 | 3 | 2.7 | 15 | 3 | 2.7
Conversational AI for Real-Life Dialogues | Pronunciation Feedback | Pronunciation Analysis | 7 | 1.4 | 1.26 | 9 | 1.8 | 1.62
Conversational AI for Real-Life Dialogues | Pronunciation Feedback | Feedback Generation | 5 | 1 | 0.9 | 7 | 1.4 | 1.26
Spaced Repetition & Revision Scheduling | Revision Scheduling | Spaced Repetition Algorithm Implementation | 8 | 1.6 | 1.44 | 10 | 2 | 1.8
Spaced Repetition & Revision Scheduling | Revision Scheduling | Scheduling User Reviews | 6 | 1.2 | 1.08 | 8 | 1.6 | 1.44
Spaced Repetition & Revision Scheduling | Lesson Summaries | Summary Generation | 7 | 1.4 | 1.26 | 9 | 1.8 | 1.62
Spaced Repetition & Revision Scheduling | Lesson Summaries | Summary Presentation | 5 | 1 | 0.9 | 7 | 1.4 | 1.26
Total |  | Total | 124 | 24.8 | 22.32 | 132 | 26.4 | 23.76
|  | Units | days | days | days | days | days | days

## Cost Summary
Item | Effort in Days | Rate per hour (IN INR) | Pricing
Frontend | 163.68 | 15 | ₹19,641.60
Backend | 174.24 | 16 | ₹22,302.72
Testing | 24.56 | 12 | ₹2,357.76
Total |  |  | ₹44,302.08