## Effort Estimation
Module | Feature | Subfeature | Frontend Effort | Frontend Buffer | Frontend Testing | Backend Effort | Backend Buffer | Backend Testing
User Authentication | Sign Up | Form Validation | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
User Authentication | Sign Up | Password Hashing | 0 | 0 | 0 | 1 | 0.2 | 0.18
User Authentication | Sign Up | Database Integration | 0 | 0 | 0 | 2 | 0.4 | 0.36
User Authentication | Login | Form Validation | 2 | 0.4 | 0.36 | 1 | 0.2 | 0.18
User Authentication | Login | Authentication API | 1 | 0.2 | 0.18 | 2 | 0.4 | 0.36
User Authentication | Password Reset | Email Verification | 2 | 0.4 | 0.36 | 2 | 0.4 | 0.36
User Authentication | Password Reset | Password Reset API | 2 | 0.4 | 0.36 | 2 | 0.4 | 0.36
Product Management | Product Listing | API Integration | 2 | 0.4 | 0.36 | 3 | 0.6 | 0.54
Product Management | Product Listing | UI/UX Implementation | 5 | 1 | 0.9 | 0 | 0 | 0
Product Management | Product Detail | API Integration | 2 | 0.4 | 0.36 | 2 | 0.4 | 0.36
Product Management | Product Detail | UI/UX Implementation | 4 | 0.8 | 0.72 | 0 | 0 | 0
Product Management | Add Product | Form Validation | 3 | 0.6 | 0.54 | 2 | 0.4 | 0.36
Product Management | Add Product | API Integration | 2 | 0.4 | 0.36 | 2 | 0.4 | 0.36
Product Management | Add Product | Database Integration | 0 | 0 | 0 | 2 | 0.4 | 0.36
Product Management | Edit Product | Form Validation | 2 | 0.4 | 0.36 | 2 | 0.4 | 0.36
Product Management | Edit Product | API Integration | 2 | 0.4 | 0.36 | 2 | 0.4 | 0.36
Product Management | Edit Product | Database Integration | 0 | 0 | 0 | 2 | 0.4 | 0.36
Total |  | Total | 32 | 6.4 | 5.76 | 29 | 5.8 | 5.22
|  | Units | days | days | days | days | days | days

## Cost Summary
Item | Effort in Days | Rate per hour (IN INR) | Pricing
Frontend | 42.24 | 15 | ₹5,068.80
Backend | 38.28 | 16 | ₹4,899.84
Testing | 6.336 | 12 | ₹608.26
Total |  |  | ₹10,576.90